## Project Planner
PratapGurung-Project3_Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | DAY STARTED | DAY FINISHED | ACTUAL DAY STARTED | ACTUAL DAY FINISHED | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Design initial ERD in SQLDBM and Project planner | 1 | 1 | 1 | 2 | 100%
Update anomalies in original table and create required schemas and to-do list | 2 | 2 | 2 | 3 | 100%
plan for indexing and each table attributes | 3 | 3 | 3 | 4 | 100%
Create WorkFlowStepTable and 7 tabels as per initial ERD desgin | 5 | 5 | 5 | 7 | 100%
ADD ADDITIONAL columns in each tables and create Store procedure to load data into each 7 tables | 8 | 8 | 9 | 9 | 100%
create stored procedure to add and drop foreign keys and to execute all 7 procedures that will load tables in one Store Procedures | 9 | 9 | 10 | 11 | 100%
Document all the tables and Stored Procedures | 11 | 12 | 12 | 12 | 100%
Create annotated PowerPoint Presentation of Project Life-cycle | 12 | 13 | 12 | 13 | 100%
Create the VHDX file and put all the files and folders on it | 13 | 13 | 13 | 14 | 100%
Submit the VHDX file | 15 | 16 | 15 | 17 | 100%