## Pratap Gurung
To-do list
To be completed by: |  | Pratap Gurung
Deadline: |  | 2019-05-13
Project 2
% done | Phase | Due By | Notes
100% | Planning | 2019-04-25 | Project planning and To-do list
100% | Preparation | 2019-04-26 | Preparation for Initial Design and update anomalies
100% | creation | 2019-04-27 | create database
100% | tables creation | 2019-04-29 | Create required schemas , 7 tables and work flow step tables
100% | Tables creation | 2019-04-25 | create all required stored procedures to load data and document procedures
100% | modification | 2019-05-05 | Add additional columns to all tables
100% | create procedure | 2019-05-06 | create a procedures that will execute all other procedures
100% | analyze | 2019-05-07 | Analyze the database using given proposition and 3 of own proposition
100% | PowerPoint | 2019-05-09 | create powerpoint with annotations of project lifecycle
100% | VHDX Submition | 2019-05-12 | Submit the all the ducumentations